## risk-register.xlsx
Risk ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | Inherent Risk Score | Existing Controls | Residual Likelihood | Residual Impact | Residual Risk Score | Owner | Mitigation Actions | Status | Review Date
ID-R01 | Ransomware attack via phishing | Cyber Threat | 4 | 5 | 20 | Email filtering, backups, training | 2 | 4 | 8 | CISO | Implement advanced EDR, regular simulations | Open | Q2 2026
ID-R02 | Data breach of customer PII due to misconfigured cloud storage | Compliance | 3 | 5 | 15 | Encryption, access controls | 2 | 3 | 6 | Compliance Lead | Annual penetration testing | Monitored | Q3 2026
ID-R03 | Third-party vendor compromise leading to supply chain attack | Supply Chain | 3 | 4 | 12 | Vendor questionnaire | 2 | 3 | 6 | Procurement | Add contract clauses, ongoing monitoring | In Progress | Monthly
ID-R04 | Insider threat -malicious employee or negligent employee leaking data | Human | 2 | 4 | 8 | Background checks, monitoring | 1 | 3 | 3 | HR | Enhanced logging for privileged users | Closed | Annual
ID-R05 | Regulatory non-compliance with SOC 2 (failed audit) | Compliance | 3 | 4 | 12 | Policies and controls in place | 2 | 3 | 6 | CISO | Perform mock audit and strengthen evidence collection | Open | Q4 2026
ID-R06 | DDoS attack causing service outage | Availability/Cyber | 3 | 4 | 12 | Basic CDN protection | 2 | 3 | 6 | IT Operations | Implement advanced DDoS mitigation service | In Progress | Q3 2026
ID-R07 | Loss of critical business data due to inadequate backups | Operational | 2 | 5 | 10 | Daily backups | 1 | 4 | 4 | IT | Test restore procedures quarterly and add geo-redundancy | In Progress | Q3 2026
ID-R08 | Phishing attack leading to credential compromise | Cyber threat | 4 | 3 | 12 | Email filtering, MFA | 2 | 2 | 4 | Security Team | Expand simulation training and deploy passwordless auth | Open | Q2 2026
ID-R09 | API vulnerability exploited by external attacker | Cyber / Application | 3 | 4 | 12 | Basic code reviews, WAF | 2 | 3 | 6 | DevSecOps | Implement API security gateway and regular pentests | Open | Q3 2026